Your Dressage Journey

Centerline Founders Launch Campaign

Marketing Plan  —  May 10 to July 7, 2026

# 1. Campaign Overview

This is a focused, founder-led, 8-week launch campaign for Your Dressage Journey (YDJ). One person can run it. The plan is structured around three locked dates that drive every decision:

- May 15, 2026 — Pilot ends. Existing pilot users move into a read-only grace window.

- June 1, 2026 — Paid tiers go live. Working, Medium, and Extended plans become purchasable.

- July 1–5, 2026 — National Dressage Pony Cup (NDPC). YDJ has a vendor table, prize partners, a printed game, and a virtual game with prize notifications.

- July 8, 2026 — Initial Centerline (IC) founder cohort closes. 100 lifetime-rate annual seats; this is the campaign’s primary money moment.

## Campaign Summary

Use NDPC as the marquee live moment to fill the Initial Centerline cohort and convert pilot users to paid tiers, anchored by a steady drip of rider and clinician YouTube content and weekly founder posts.

## Primary Objective (SMART)

Enroll 50 of the 100 Initial Centerline annual seats by 11:59pm on July 7, 2026.

Why 50: it is ambitious for a solo launch but well below the 100 cap, leaving room for a final-week surge from NDPC and the closing email push. Adjust upward if pilot conversion runs hot in the first two weeks.

## Secondary Objectives

- Convert at least 30% of active pilot users to a paid monthly or annual tier by July 7.

- Grow the YDJ email list by 500 subscribers (mostly from NDPC and YouTube).

- Make all 15 YouTube videos public on a release schedule and gain 250 channel subscribers.

- Capture 75 in-person email signups at the NDPC booth.

# 2. Target Audience

## Primary: Adult Amateur Dressage Riders

Mid-30s to early-60s. Riding and showing at Training through PSG. They keep notebooks, voice memos, or scattered journals — or they wish they did. They are frustrated by the gap between weekly lessons and what they actually remember a week later. They follow specific clinicians on YouTube, belong to USDF and a regional GMO, are active in two or three Facebook dressage groups, and lurk on Chronicle of the Horse forums.

### Pain Points

- “I know I learned something at that lesson, but I can’t get back to it on Tuesday.”

- “My coach can’t see what I did between sessions, so we keep starting over.”

- “I journal sometimes, but no one ever reads it back — including me.”

- “I feel things in my body during a ride and they vanish before I can name them.”

### Where They Spend Time

- Facebook: Adult Amateur Dressage, USDF, regional GMO groups, breed-specific dressage groups.

- YouTube: clinicians, training channels, ride-along videos.

- Instagram: barn life, show recaps, training reels.

- In person: clinics, schooling shows, USDF rated shows, NDPC.

## Secondary: Active Pilot Users

Already convinced of the input experience. Need a confident, warm hand-off into a paid tier with a real reason to choose Initial Centerline now (lifetime founder rate, 6-month upgrade window, scarcity).

## NDPC-Specific Audience

Pony Cup competitors and their support people skew tight-knit, social, and word-of-mouth driven. Smaller community than open dressage — a great seed audience. The vendor table, printed game, and on-site prizes are specifically built for this in-person moment.

# 3. Key Messages

## Core Message

Stop journaling into a void. YDJ turns your reflections into coaching that actually remembers — across every ride, every horse, every season.

## Supporting Messages

### 1. The cross-data pattern story

“You can’t hold every ride, every reflection, and every health note in your head. YDJ can. It looks across all of it and shows you what you’ve been too close to see.”

### 2. The four-voices story

“One platform, four coaching voices: a Classical Master, an Empathetic Coach, a Technical Coach, and a Practical Strategist. Same data, four lenses — read whichever voice you need that week.”

### 3. The built-by-an-amateur story

“Built by a 20+ year adult amateur for adult amateurs. Not a pro’s system retrofit. Designed for the rider who fits training around real life.”

### 4. The founder-rate scarcity story (used June 1 onward)

“100 Initial Centerline seats. Lifetime founder rate while you stay subscribed. After July 8, this rate is gone forever.”

## Proof Points

- Pilot rider quotes captured during the Feb–May pilot (anonymized, with permission).

- Clinician video reflections (your existing 15 YouTube videos).

- Founder credibility: 20+ years in dressage, building this from inside the discipline.

- Six-category reflection framework grounded in skill development research.

# 4. Channel Strategy

Eight channels, ranked by leverage for a one-person team. Owned channels (YouTube, email, social) carry the campaign; earned channels (NDPC partner posts, dressage groups) extend reach for free; paid is used surgically to amplify what is already working.

| Channel | Why it fits | Format | Effort | Spend |
| --- | --- | --- | --- | --- |
| YouTube (owned) | Existing 15-video bank of riders + clinicians answering reflection questions — use as the campaign’s anchor library. | Schedule public releases 2x/week | Low | $0 |
| Email (owned) | Pilot users + new captures are the warmest IC audience. Email is the conversion workhorse. | Newsletter + sequence | Medium | $0–$100 |
| Instagram + Facebook (owned) | Founder-led posts and Reels reach the dressage community. Strong fit for behind-the-scenes NDPC content. | Reels, carousels, stories | Medium | $0 |
| NDPC partner posts (earned) | Pre-event posts on NDPC pages put YDJ in front of every attendee before they arrive. | Image post + short caption | Low | $0 |
| Facebook dressage groups (earned) | Targeted, helpful presence in 3–5 groups builds organic credibility. Be useful, never spammy. | Comments + occasional shares | Medium | $0 |
| Meta paid ads | Highly targetable to dressage interests. Best for amplifying your strongest founder post and for retargeting site visitors. | Boosted founder posts + retargeting | Medium | $300–$500 |
| NDPC booth (paid + earned) | The marquee moment. Physical game, prize draw, virtual game launch, in-person email captures. | Vendor table + signage + game | High | $300–$500 |
| Print collateral | Postcards, table sign, business cards, NDPC handout with QR + IC offer code. | Print | Low | $150–$250 |

## Selection Notes

- YouTube videos are your most underused asset. Releasing them on a schedule — not all at once — gives the campaign a steady cadence and reduces solo content production load.

- Avoid spreading thin: skip TikTok, podcast guesting, and PR pitches this round. They cost time you do not have.

- Founder visibility is on — plan a short founder Reel or Live each week. This is the highest-trust lever for an indie launch.

# 5. Content Calendar (May 10 – July 7)

Nine-week, week-by-week plan. Each week has one theme to keep your solo focus clean. Bold spend rows are when you commit dollars.

| Week | Dates | Theme | Activities | Channels | Spend |
| --- | --- | --- | --- | --- | --- |
| W1 | May 11–17 | Foundation | • Lock IC pricing page + Stripe coupons (test → live) • Polish website hero, navigation, FAQ • Set up email capture + welcome flow • Pick top 3 anchor YouTube videos for first releases • Send pilot retention email: “May 15 is coming, here’s what’s next” | Website Email Stripe | $0 |
| W2 | May 18–24 | Pilot Sunset + IC Soft Launch | • May 15 pilot ended — send pilot conversion email #1 (warm thank-you + IC offer) • Make Anchor Video #1 public on YouTube (most universally appealing) • Founder IG/FB post: “Why I built this” founder story • Personal DMs to 10 most-engaged pilot users • Submit NDPC pre-event post draft to organizers, request June 8–15 window | Email YouTube IG/FB DM | $0 |
| W3 | May 25–31 | IC Visibility Push | • Make Anchor Video #2 public (Aha Moment category) • Public IC announcement post on IG/FB + email • Boost top-performing founder post: $50–$100 • Soft-test virtual YDJ game with 2–3 friends, fix any prize-notification bugs • Dressage Facebook group: post one helpful comment thread per group (no link drops) | YouTube Email Meta ads Game FB groups | $50–$100 |
| W4 | Jun 1–7 | Go-Live Week | • June 1: official paid go-live announcement (email blast + IG/FB) • Transparent founder post on a dressage forum (“I built this”) • Make Anchor Video #3 public (Connection / partnership) • Launch Meta retargeting ads: $50–$75 • Pilot conversion email #2 (countdown framing: 5 weeks until IC closes) | Email Forum YouTube Meta ads | $75–$125 |
| W5 | Jun 8–14 | NDPC Hype Build | • Confirm NDPC pre-event partnership post is scheduled • Make Video #4 public (Obstacle / relatable struggle) • Founder “Meet me at NDPC” Reel or Live • Confirm prize fulfillment with vendor partners (count, condition, packaging) • Order print collateral: postcards, business cards, table signage | NDPC YouTube IG/FB Live Print | $150–$250 |
| W6 | Jun 15–21 | Game + Community | • Make Video #5 public (External Validation / clinician) • Publicly launch the virtual YDJ game (link via website + email) • Sweepstakes tease: “Play the YDJ game at NDPC for prizes” • Engage in 3–5 Facebook dressage group threads with genuine value • Capture 5 short pilot user testimonials on video for July use | YouTube Game Email FB groups | $0 |
| W7 | Jun 22–28 | Final Pre-NDPC Push | • Make Video #6 public (Personal Milestone) • Email: “What I’m bringing to NDPC + IC closes July 8” • Refresh Meta ad creative (top performer + new founder testimonial cut) • Pack vendor table essentials: signage, postcards, game, QR code stand, charger • Schedule daily NDPC posts in a draft folder so you only hit ‘post’ on-site | Email Meta ads YouTube Logistics | $75–$150 |
| W8 | Jun 29–Jul 5 | NDPC Week | • Travel + table setup • Daily IG/FB stories from booth • Capture rider testimonials at booth (use later) • Run physical YDJ game + prize draws on a posted schedule • Email between sessions: “Live from NDPC, X IC spots left” | NDPC booth IG/FB stories Email | $0 |
| W9 | Jul 6–7 | Final Sprint to IC Close | • Recap post: photos + quotes from NDPC • Final 48-hour IC reminder email morning of July 6 • Founder thank-you video, posted to IG/FB/YouTube • July 7 EOD: switch IC banner on website to “Closed” • Make Video #7 public to keep YouTube cadence going post-campaign | Email IG/FB Website | $0 |

## Production Cadence Tip

Pick one weekday morning each week (suggest Monday) for content production: writing posts, scheduling YouTube release, drafting that week’s email. Outside that block, you are not making content — you are running the business.

# 6. Content Pieces Needed

| Asset | Type | Priority | Target date |
| --- | --- | --- | --- |
| IC pricing page | Landing page section | Must-have | May 17 |
| Pilot conversion email sequence (3 emails) | Email | Must-have | May 17 (E1) → Jul 6 (E3) |
| NDPC pre-event partnership post | Image + caption | Must-have | Jun 8 (delivered to NDPC) |
| Founder “Why I built this” post | IG/FB carousel or Reel | Must-have | May 18 |
| Meta ad creative — 2 variations | Image + 2 captions | Must-have | May 25 |
| Print postcards with NDPC offer code | Print, 4x6 | Must-have | Order by Jun 12 |
| Booth signage (table banner + QR sign) | Print | Must-have | Order by Jun 12 |
| Virtual game launch email | Email | Must-have | Jun 15 |
| NDPC daily stories pack (10 templates) | IG/FB stories | Must-have | Drafted by Jun 28 |
| Founder “Meet me at NDPC” Reel | Short video | Must-have | Jun 10 |
| NDPC recap email + post | Email + IG/FB | Must-have | Jul 6 |
| Founder thank-you video | Short video | Nice-to-have | Jul 7 |
| Pilot testimonial video cuts (3–5) | Short video | Nice-to-have | Jun 22 |

# 7. Success Metrics

| Metric | Target by Jul 7 | How tracked | Cadence |
| --- | --- | --- | --- |
| Initial Centerline sign-ups | 50 of 100 | Stripe + Firestore IC counter | Daily |
| Pilot → paid conversion rate | ≥ 30% of active pilots | Firestore: subscriptionTier transitions | Weekly |
| Email list growth | +500 net subscribers | Email tool dashboard | Weekly |
| YouTube subscribers | +250 net | YouTube Studio | Weekly |
| NDPC booth email captures | ≥ 75 | Tally on a clipboard + post-event entry | Daily during NDPC |
| Virtual game plays | ≥ 200 | In-app counter | Weekly |
| Meta ads cost per click | < $1.50 | Meta Ads Manager | Weekly during run |
| Founder post engagement rate | ≥ 5% on top 3 posts | IG/FB insights | Weekly |

## Reporting Cadence

Sunday evening, 30 minutes: write a 5-line update in a running notes file — sign-ups this week, top post, what surprised you, what to change next week. That is your only required reporting.

# 8. Budget Allocation

Working budget: $1,200 (midpoint of your $500–$2,000 range). Front-loaded toward the two highest-leverage moments: the W3–W4 ad amplification and the NDPC week.

| Bucket | Allocation | Notes |
| --- | --- | --- |
| Meta paid ads | $400 | Boost the single best-performing founder post (W3), then retargeting ads in W4 + W7. Pause if CPC > $2. |
| NDPC print + signage | $300 | Postcards (250), table banner, business cards, QR stand. |
| NDPC prize fulfillment top-ups | $150 | Small extras to round out vendor donations — ribbons, branded notebooks, a hospitality basket. |
| Email tool month upgrade (if needed) | $100 | One paid month of Mailerlite or similar to handle list growth + segmentation. |
| Contingency | $250 | Reactive boosts, unexpected printing, last-minute travel needs. |
| Total | $1,200 | Within the $500–$2,000 range, leaves room to flex up if a channel is over-performing. |

If you have to cut: drop the email-tool upgrade first ($100) and trim ad spend to $250. NDPC print and prize budget should be protected — it is the campaign’s physical credibility.

# 9. Risks and Mitigations

### Risk: Solo bandwidth crunch

One person cannot run paid ads, write content, manage a booth, and answer support all in the same week. Mitigation: batch content into a single weekly production block (suggest Monday morning), schedule everything in advance, and accept that NDPC week is exec-mode only — nothing new gets created on-site.

### Risk: NDPC booth weather, crowd, or logistics disruption

If foot traffic is lower than hoped, lean harder on the virtual YDJ game and digital channels for that week. Pre-stage the daily NDPC story templates so they post even if the booth is quiet.

### Risk: IC adoption slow through mid-June

If IC sign-ups are below 20 by June 15, run a 1-day founder “office hours” Live, send a personal email to every active pilot user with their name and one specific pattern from their data, and double the W7 ad budget.

### Risk: Pilot users feel pushed

Mitigation: every pilot conversion email leads with appreciation, explains the grace window clearly, and gives an honest “no hard feelings if you skip” opt-out line. The pilot relationship is more valuable than any single conversion.

# 10. Next Steps (This Week, May 11–17)

- Lock IC Stripe coupons in test mode by May 13, then promote to live.

- Finalize the IC pricing page and the FAQ section by May 17.

- Email NDPC organizers to confirm the June 8–15 partnership-post window.

- Choose the 3 anchor YouTube videos for W2, W3, W4 releases. Write captions for each.

- Pull a list of the top 10 most-engaged pilot users for personal DMs in W2.

- Block off Monday mornings on your calendar for the next 9 weeks as content production time.

- Open a single running file (Notes app or Google Doc) for your Sunday 5-line weekly update.

## Want me to go deeper?

Happy to draft the actual pilot conversion email sequence, the founder “Why I built this” post, NDPC postcard copy, the IC pricing page hero copy, or a tighter visual ad creative brief. Just say which one to start with.